## 2010.09.07
# | Name | Description | References
1 | Product Backlog | The product backlog (or "backlog") is the requirements for a system, expressed as a prioritized list of product backlog Items. These included both functional and non-functional customer requirements, as well as technical team-generated requirements. While there are multiple inputs to the product backlog, it is the sole responsibility of the product owner to prioritize the product backlog. | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1125 http://blog.mountaingoatsoftware.com/tag/product-backlog http://www.mountaingoatsoftware.com/product-backlog
2 | Sprint Backlog | Defines the work for a sprint, represented by the set of tasks that must be completed to realize the sprint's goals, and selected set of product backlog items. | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1117 http://blog.mountaingoatsoftware.com/tag/sprint-backlog
3 | Release Backlog | This term sometime is used as a mean of portion of product backlog considered to be a part of release. It is not a core scrum practice. | http://blog.mountaingoatsoftware.com/why-there-should-not-be-a-release-backlog
4 | Product Backlog Item | In Scrum, a product backlog item ("PBI", "backlog item", or "item") is a unit of work small enough to be completed by a team in one Sprint iteration. Backlog items are decomposed into one or more tasks. | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1130 http://blog.mountaingoatsoftware.com/tag/user-stories
5 | Task | In Scrum, a sprint task (or task) is a unit of work generally between four and sixteen hours. Team members volunteer for tasks. They update the estimated number of hours remaining on a daily basis, influencing the sprint Burndown chart. Tasks are contained by backlog items. | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1129
6 | Release | The transition of an increment of potentially shippable product from the development team into routine use by customers. Releases typically happen when one or more sprints has resulted in the product having enough value to outweigh the cost to deploy it. | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1120
7 | Product Owner | A single person must have final authority representing the customer's interest in backlog prioritization and requirements questions. | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms http://blog.mountaingoatsoftware.com/tag/product-owner
8 | The Team | The team is optimally comprised of seven plus or minus two people. For software development projects, the team members are usually a mix of software engineers, architects, programmers, analysts, QA experts, testers, UI designers, etc. This is often called "cross-functional project teams". Agile practices also encourage cross-functional team members. | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1122
9 | Team Member | Anyone working on sprint tasks toward the sprint goal | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1111
10 | Scrum Master | The Scrum Master is a facilitator for the team and product owner. Rather than manage the team, the Scrum Master works to assist both the team and product owner | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1121
11 | The Scrum Team | Contains The Team, Scrum Master and Product Owner | http://portal/sites/delivery/SrvAgile/Document%20Library/1/Materials/Documentation/Scrum%20Guide.pdf
12 | Scrum of Scrums | Group of scrum masters organized to handle issues/dependencies across scrum teams. Usually have weekly meetings. | http://www.mountaingoatsoftware.com/pages/13-scrum-team-training http://www.mountaingoatsoftware.com/articles/35-advice-on-conducting-the-scrum-of-scrums-meeting
13 | Product Backlog Sizing | Sometime called as estimation of stories. This is giving the backlog items/stories relative estimates. Happens on separate meeting. | http://blog.mountaingoatsoftware.com/tag/agile-estimation
14 | Planning Poker | The game played to estimate/size product backlog items/stories | http://www.mountaingoatsoftware.com/pages/26-planning-pokeran-agile-estimating-technique-for-agile-and-scrum-teams
15 | Sprint Planning 1 | The Sprint planning meeting is a negotiation between the team and the product owner about what the team will do during the next sprint. Often happens before sprint planning 2 to resize product backlog items, analyze backlog items, make commitments. Sometime, planning poker is repeated at this stage. | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1114 http://blog.mountaingoatsoftware.com/when-should-we-estimate-the-product-backlog
16 | Sprint Planning 2 | The Sprint planning meeting is a negotiation between the team and the product owner about what the team will do during the next sprint. Backlog items are being broken down and estimated in hours. | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1114
17 | Daily Standup/Scrum | A fifteen-minute daily meeting for each team member to answer three questions (what's done, what's planned, what's blocking) | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1128 http://blog.mountaingoatsoftware.com/tag/daily-standup
18 | Sprint Review | The meeting arranged for Team to demo the backlog items developed to Product Owner for accepting. | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1115 http://www.mountaingoatsoftware.com/pages/16-scrum-team-conducts-sprint-review-meeting
19 | Sprint Retrospective | The meeting arranged to discuss Pros, Cons and what to improve. Happens at the end of each sprint. Could be used for releases too. | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1113
20 | Chief Product Owner | Head of PO organization if more then 1. Have a last call. | http://www.infoq.com/articles/agile-product-owner
21 | Product Backlog Item Effort | Estimate of the effort of product backlog items | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1109
22 | Story Points | Type of estimate of the effort of product backlog items, most popular in Scrum | http://en.wikipedia.org/wiki/Story_points http://blog.mountaingoatsoftware.com/tag/story-points
23 | Ideal Days | Type of estimate of the effort of product backlog items, very popular in Scrum | http://blog.mountaingoatsoftware.com/should-companies-measure-productivity-in-story-points-ideal-days http://en.wikipedia.org/wiki/Story_points#Ideal_Days_Basis
24 | Release Burndown Chart | The release Burndown chart is a "big picture" view of a release's progress. | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1123 http://blog.mountaingoatsoftware.com/improving-on-traditional-release-burndown-charts
25 | Sprint Burndown Chart | A sprint Burndown chart (or "sprint Burndown graph") depicts the total task hours remaining per day | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1116
26 | Release Planning Meeting | The purpose of release planning is to establish a plan and goals that the Scrum Teams and the rest of the organizations can understand and communicate. | http://portal/sites/delivery/SrvAgile/Document%20Library/1/Materials/Documentation/Scrum%20Guide.pdf
27 | Velocity | In Scrum, velocity is how much product backlog effort a team can handle in one sprint. | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1110 http://blog.mountaingoatsoftware.com/tag/velocity
28 | Business Value | A value, often from 0 to 40 which represents the 'priority' of backlog item, what it gives to the product | http://www.agile-software-development.com/2009/02/measuring-business-value-in-agile.html
29 | Scrum values | five values, not in the order: Commitment, Focus, Openness, Respect and Courage. | http://www.implementingscrum.com/2008/03/25/scrum-values-learn-them-live-them/
30 | Sprint Goal | Sprint goals are the result of a negotiation between the product owner and the development team | http://www.scrumalliance.org/articles/39-glossary-of-scrum-terms#1115
31 | Abnormal Sprint Termination | Cancelation of a Sprint if Team feels they are unable to meet the Sprint Goal | http://en.wikipedia.org/wiki/Scrum_(development)#Others
32 | Definition of Done | The set of rules that represents when Team assume backlog item is done. Usually includes Dev, QA, Doc, Peer Review, Unit Testing etc. | http://www.scrumalliance.org/articles/107-how-do-we-know-when-we-are-done
33 | Acceptance Criteria | Acceptance criteria are the requirements that have to be met for a story to be assessed as complete | http://scrummethodology.com/scrum-acceptance-criteria/
34 | Task breakdown | Breaking Stories/Product Backlog items into tasks | http://www.agile-software-development.com/2007/10/how-to-implement-scrum-in-10-easy-steps_11.html
35 | Sprint Length | Duration of sprint in weeks from 1 to 4 | http://www.scrumalliance.org/articles/10-rethinking-sprint-length
36 | T-Shirt estimates | Estimation of backlog items in values of XS, S, M, L, XL, XXL etc | http://30secondblogs.blogspot.com/2006/10/t-shirt-estimates.html
37 | Spike | A spike is an experiment that allows developers to learn just enough about something unknown in a user story, e.g. a new technology, to be able to estimate that user story. A spike must be time-boxed. This defines the maximum time that will be spent learning and fixes the estimate for the spike. | http://www.extremeprogramming.org/rules/spike.html
38 | 80/20 rule | Pareto principle. Seeking to focus on the important 20% of effort that gets the majority of the results (80%). | http://www.agile-software-development.com/2007/04/agile-principle-8-enoughs-enough.html http://en.wikipedia.org/wiki/Pareto_principle
39 | Sprint 0 | Sprint 0 sometime is used before Sprint 1 to clarify the product backlog, do Proof of Concepts, analysis etc before release kick-off. There is no unique opinion whether it is core scrum or not. | http://www.infoq.com/news/2008/09/sprint_zero
40 | Stabilization sprint/hardening sprint | This represents the sprint to stabilize the code, fix bugs in complex products. Happens at the end of release to make potentially shippable product actually shippable. | http://www.infoq.com/news/2008/02/done-shippable-quality
41 | Distributed Team | Team that is not collocated. There are a lot of risks around that so there is also a big theory about mitigation them. Should be always in mind. | http://www.scrumalliance.org/resource_download/17 http://blog.mountaingoatsoftware.com/tag/distributed-teams
42 | The Chicken and the Pig | Committed (pig) is the equivalent of A(countable) and R(responsible) Involved (chicken) is the equivalent of C(onsults) and I(nformed) | http://en.wikipedia.org/wiki/The_Chicken_and_the_Pig http://www.agilemanagement.net/Articles/Weblog/ChickensandPigs.html
43 | 5 Whys | The 5 Whys is a question-asking method used to explore the cause/effect relationships underlying a particular problem. Ultimately, the goal of applying the 5 Whys method is to determine a root cause of a defect or problem. | http://en.wikipedia.org/wiki/5_Whys
44 | Defect backlog | I also called bug backlog, a list of bugs found that are not related to current features. Could be attacked during hardening sprints or each sprint a portion.
45 | Time-Boxes | The Time-Boxes in Scrum are the Release Planning Meeting, the Sprint, the Sprint Planning Meeting, the Sprint Review, the Sprint Retrospective, and the Daily Scrum. | http://portal/sites/delivery/SrvAgile/Document%20Library/1/Materials/Documentation/Scrum%20Guide.pdf
46 | Agile Manifesto | a statement of the principles that underpin agile software development | http://agilemanifesto.org/